## V1
Cost Baseline V1
Project Name: WeBook | Date: 16/10/2021
Note: Enter your WBS and costs each month. Add/delete rows and columns as needed and check all formulas (bolded below).
Weeks
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | Total Cost
WBS Categories
1. Requirement Phase
1.1 Team Bonding | 214.29 | [6 empty] | 214.29
1.2 Project Charter | 428.57 | [6 empty] | 428.57
1.3 CIO Approval | 17.86 | [6 empty] | 17.86
1.4 Project Scope | 321.43 | [6 empty] | 321.43
1.5 Team Scope
1.6 Risk Management
1.7 Purchase Computers | 9000 | [6 empty] | 9000
1.8 Learn Basic Coding | 6000 | [6 empty] | 6000
1.9 Learn Basic GUI | 6000 | [6 empty] | 6000
1.10 Requirements Complete
2. Coding Phase
2.1 Coding of Student End |  | 1428.58 | [5 empty] | 1428.58
2.2 Coding of Staff End |  | 1428.58 | [5 empty] | 1428.58
2.3 Coding Complete
3. Integration Phase
3.1 Convert C++ into Python |  |  | 857.14 |  |  |  |  | 857.14
3.2 Display code in GUI |  |  | 571.43 |  |  |  |  | 571.43
3.3 Integration Complete
4. Testing Phase
4.1 Testing Student End |  |  |  | 285.71 |  |  |  | 285.71
4.2 Testing Staff End |  |  |  | 285.71 |  |  |  | 285.71
4.3 Testing Integrated Codes |  |  |  | 571.43 |  |  |  | 571.43
4.4 Testing Codes on GUI |  |  |  | 285.71 |  |  |  | 285.71
4.5 Testing Complete
5. Documentation Phase
5.1 Prepare Report |  |  |  |  | 571.43 |  |  | 571.43
5.2 Prepare Video |  |  |  |  | 571.43 |  |  | 571.43
5.3 Prepare Deliverables |  |  |  |  | 571.43 |  |  | 571.43
5.4 Prepare for Q&A with CIO |  |  |  |  | 571.43 |  |  | 571.43
5.5 Quality Control Checking |  |  |  |  | 285.71 |  |  | 285.71
5.6 Documentation Complete
6. Project Closing
6.1 Submission of Report | [5 empty] | 285.71 |  | 285.71
6.2 Submission of Video | [5 empty] | 285.71 |  | 285.71
6.3 Submission of Deliverables | [5 empty] | 285.71 |  | 285.71
6.4 Project Close
6.5 Office Payment
6.5.1 Office Payment 1 | 1000 | [6 empty] | 1000
6.5.2 Office Payment 2 |  | 1000 | [5 empty] | 1000
6.5.3 Office Payment 3 |  |  | 1000 |  |  |  |  | 1000
6.5.4 Office Payment 4 |  |  |  | 1000 |  |  |  | 1000
6.5.5 Office Payment 5 |  |  |  |  | 1000 |  |  | 1000
6.5.6 Office Payment 6 | [5 empty] | 1000 |  | 1000
7. Team Meeting
7.1 Team Meeting 1 | 857.14 | [6 empty] | 857.14
7.2 Team Meeting 2 |  | 857.14 | [5 empty] | 857.14
7.3 Team Meeting 3 |  |  | 857.14 |  |  |  |  | 857.14
7.4 Team Meeting 4 |  |  |  | 857.14 |  |  |  | 857.14
7.5 Team Meeting 5 |  |  |  |  | 857.14 |  |  | 857.14
7.6 Team Meeting 6 | [5 empty] | 857.14 |  | 857.14
7.7 Team Meeting 7 | [6 empty] | 857.14 | 857.14
Total | 23839.29 | 4714.3 | 3285.71 | 3285.7 | 4428.57 | 2714.27 | 857.14 | 43124.98 | Cost estimate--> | $43,124.98
*Reserves are all entered in month 12

## V2
Cost Baseline V2
Project Name: WeBook | Date: 22/10/2021
Note: Enter your WBS and costs each month. Add/delete rows and columns as needed and check all formulas (bolded below).
Weeks
| 1 | 2 | 3 | 4 | 5 | 6 | 7 | Total Cost
WBS Categories
1. Requirement Phase
1.1 Team Bonding | 214.29 | [6 empty] | 214.29
1.2 Project Charter | 428.57 | [6 empty] | 428.57
1.3 CIO Approval | 17.86 | [6 empty] | 17.86
1.4 Project Scope | 321.43 | [6 empty] | 321.43
1.5 Team Scope
1.6 Risk Management
1.7 Purchase Computers | 9000 | [6 empty] | 9000
1.8 Learn Basic Coding | 6000 | [6 empty] | 6000
1.9 Learn Basic GUI | 6000 | [6 empty] | 6000
1.10 Requirements Complete
2. Coding Phase
2.1 Coding of Student End |  | 1428.58 | [5 empty] | 1428.58
2.2 Coding of Staff End |  | 1428.58 | [5 empty] | 1428.58
2.3 Coding of System Administrator End |  | 1428.58 | [5 empty] | 1428.58
2.4 Coding Complete
3. Integration Phase
3.1 Convert C++ into Python |  |  | 857.14 |  |  |  |  | 857.14
3.2 Display code in GUI |  |  | 571.43 |  |  |  |  | 571.43
3.3 Integration Complete
4. Testing Phase
4.1 Testing Student End |  |  |  | 285.71 |  |  |  | 285.71
4.2 Testing Staff End |  |  |  | 285.71 |  |  |  | 285.71
4.3 Testing System Administrator End |  |  |  | 285.71 |  |  |  | 285.71
4.4 Testing Integrated Codes |  |  |  | 571.43 |  |  |  | 571.43
4.5 Testing Codes on GUI |  |  |  | 285.71 |  |  |  | 285.71
4.6 Testing Complete
5. Documentation Phase
5.1 Prepare Report |  |  |  |  | 571.43 |  |  | 571.43
5.2 Prepare Video |  |  |  |  | 571.43 |  |  | 571.43
5.3 Prepare Deliverables |  |  |  |  | 571.43 |  |  | 571.43
5.4 Prepare for Q&A with CIO |  |  |  |  | 571.43 |  |  | 571.43
5.5 Quality Control Checking |  |  |  |  | 285.71 |  |  | 285.71
5.6 Documentation Complete
6. Project Closing
6.1 Submission of Report | [5 empty] | 285.71 |  | 285.71
6.2 Submission of Video | [5 empty] | 285.71 |  | 285.71
6.3 Submission of Deliverables | [5 empty] | 285.71 |  | 285.71
6.4 Project Close
6.5 Office Payment
6.5.1 Office Payment 1 | 1000 | [6 empty] | 1000
6.5.2 Office Payment 2 |  | 1000 | [5 empty] | 1000
6.5.3 Office Payment 3 |  |  | 1000 |  |  |  |  | 1000
6.5.4 Office Payment 4 |  |  |  | 1000 |  |  |  | 1000
6.5.5 Office Payment 5 |  |  |  |  | 1000 |  |  | 1000
6.5.6 Office Payment 6 | [5 empty] | 1000 |  | 1000
6.5.7 Office Payment 7 | [6 empty] | 1000 | 1000
7. Team Meeting
7.1 Team Meeting 1 | 857.14 | [6 empty] | 857.14
7.2 Team Meeting 2 |  | 857.14 | [5 empty] | 857.14
7.3 Team Meeting 3 |  |  | 857.14 |  |  |  |  | 857.14
7.4 Team Meeting 4 |  |  |  | 857.14 |  |  |  | 857.14
7.5 Team Meeting 5 |  |  |  |  | 857.14 |  |  | 857.14
7.6 Team Meeting 6 | [5 empty] | 857.14 |  | 857.14
7.7 Team Meeting 7 | [6 empty] | 857.14 | 857.14
Total | 23839.29 | 6142.88 | 3285.71 | 3571.41 | 4428.57 | 2714.27 | 1857.14 | 45839.27
*Reserves are all entered in month 12