## V1
Cost Estimate
Project Name: WeBook | Date: 16/10/2021
Note: Enter your WBS, hours, labor rates, etc. Add/delete rows and columns as needed and check all formulas (bolded below).
| Internal | $/Day | Members Involved | External | External | External | Total | Total | Non-labor $ | Total Cost
WBS Categories | Labor |  |  | Labor |  | $ Total | Labor | Labor |  | $43,125.02
Requirement Phase | [6 empty] | - |  |  | $21,982.14
Team Bonding | 0.0833 days | $149 | 6 |  |  |  | 214.29 |  |  | $214.29
Project Charter | 0.1667 days | $149 | 6 |  |  |  | 428.57 |  |  | $428.57
CIO Approval | 0.0417 days | $149 | 1 |  |  |  | 17.86 |  |  | $17.86
Project Scope | 0.125 days | $149 | 6 |  |  |  | 321.43 |  |  | $321.43
Purchase Computers | 1 day | [5 empty] | - |  | $9,000.00 | $9,000.00
Learn Basic Coding | 0 days | $149 | 6 |  |  |  | 6000 |  |  | $6,000.00
Learn Basic GUI | 7 days | $149 | 6 |  |  |  | 6000 |  |  | $6,000.00
Requirements Complete | 7 days | $149 |  |  |  |  | $0.00 |  |  | $0.00
Coding Phase | 5 days | [5 empty] | - |  |  | $2,857.16
Coding of Student End | 5 days | $149 | 2 |  |  |  | 1428.58 |  |  | $1,428.58
Coding of Staff End | 5 days | $149 | 2 |  |  |  | 1428.58 |  |  | $1,428.58
Coding Complete | 0 days | [5 empty] | 0 |  |  | $0.00
Integration Phase | [6 empty] | - |  |  | $1,428.57
Convert C++ into Python | 3 days | $149 | 2 |  |  |  | 857.14 |  |  | $857.14
Display code in GUI | 2 days | $149 | 2 |  |  |  | 571.43 |  |  | $571.43
Integration Complete | 0 days | [5 empty] | 0 |  |  | $0.00
Testing Phase | [6 empty] | - |  |  | $1,428.57
Testing Student End | 1 day | $149 | 2 |  |  |  | 285.71 |  |  | $285.71
Testing Staff End | 1 day | $149 | 2 |  |  |  | 285.71 |  |  | $285.71
Testing Integrated Codes | 2 days | $149 | 2 |  |  |  | 571.43 |  |  | $571.43
Testing Codes on GUI | 1 day | $149 | 2 |  |  |  | 285.71 |  |  | $285.71
Testing Complete | 0 days | [5 empty] | 0 |  |  | $0.00
Documentation Phase | [6 empty] | - |  |  | $2,571.43
Prepare Report | 2 days | $149 | 2 |  |  |  | 571.43 |  |  | $571.43
Prepare Video | 2 days | $149 | 2 |  |  |  | 571.43 |  |  | $571.43
Prepare Delivarables | 2 days | $149 | 2 |  |  |  | 571.43 |  |  | $571.43
Prepare for Q&A with CIO | 2 days | $149 | 2 |  |  |  | 571.43 |  |  | $571.43
Quality Control Checking | 1 day | $149 | 2 |  |  |  | 285.71 |  |  | $285.71
Documentation Complete | 0 days | [5 empty] | 0 |  |  | $0.00
Project Closing | [6 empty] | - |  |  | $6,857.14
Submission of Report | 1 day | $149 | 2 |  |  |  | 285.71 |  |  | $285.71
Submission of Video | 1 day | $149 | 2 |  |  |  | 285.71 |  |  | $285.71
Submission of Deliverables | 1 day | $149 | 2 |  |  |  | 285.71 |  |  | $285.71
Project Close | 0 days | [5 empty] | 0 |  |  | $0.00
Office Payment | [6 empty] | - |  |  | $6,000.00
Office Payment 1 | 0 days | [7 empty] | $1,000.00 | $1,000.00
Office Payment 2 | 0 days | [7 empty] | $1,000.00 | $1,000.00
Office Payment 3 | 0 days | [7 empty] | $1,000.00 | $1,000.00
Office Payment 4 | 0 days | [7 empty] | $1,000.00 | $1,000.00
Office Payment 5 | 0 days | [7 empty] | $1,000.00 | $1,000.00
Office Payment 6 | 0 days | [7 empty] | $1,000.00 | $1,000.00
Team Meeting | [6 empty] | - |  |  | $6,000.00
Team Meeting 1 | 1 day | $149 | 6 |  |  |  | 857.14 |  |  | $857.14
Team Meeting 2 | 1 day | $149 | 6 |  |  |  | 857.14 |  |  | $857.14
Team Meeting 3 | 1 day | $149 | 6 |  |  |  | 857.14 |  |  | $857.14
Team Meeting 4 | 1 day | $149 | 6 |  |  |  | 857.14 |  |  | $857.14
Team Meeting 5 | 1 day | $149 | 6 |  |  |  | 857.14 |  |  | $857.14
Team Meeting 6 | 1 day | $149 | 6 |  |  |  | 857.14 |  |  | $857.14
Team Meeting 7 | 1 day | $149 | 6 |  |  |  | 857.14 |  |  | $857.14
Total | 49.38 days |  |  | 0 | 0 | 0 | 28124.98 | 0 | $15,000 | $43,124.98
Assumptions