## Risk Register
Risk Register for Webook
Date 9/10/21
Project Name: Webook
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 6 | Risk of team member leaving from group | HR | Each member is paired with a secondary role as a contigency | Christie | L | H | NIL
2 | 7 | Risk of team member joining group | HR | PM will have to get new member up to date and allocate them roles | Christie | L | L | NIL
3 | 2-Delete when risk is solved | Risk of unfamiliarity with programming language | Technology | Learn more than 1 programming language | Danial, Tian Sheng | M | H | Unable to find alternatives
4 | 1 | Risk of scope requirements not met | Deliverable | Weekly meetings for updating and tracking progress | Danial, Whye Keat | M | H | NIL
5 | 3-Delete when risk is solved | Risk of failed integration of coding | Technology | Acquire skill in technologies, information, and processes | Whye Keat, Yong Qi | M | H | Unable to have a working prototype
6 | 8 | Risk of exceeding budget | Finance | Properly manage finance | Hui Min | L | L | NIL
7 | 4 | Risk of not meeting project schedule | Administrative | Track the progress of project weekly | Hui Min | L | H | NIL
8 | 5 | Risk of overall poor project quality | Deliverable | Conduct more quality checks of project inputs and outputs | Tian Sheng, Yong Qi | L | H | NIL
9
Risk Register for Webook V2
Date 22/10/21
Project Name: Webook
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 6 | Risk of team member leaving from group | HR | Each member is paired with a secondary role as a contigency | Christie | L | H | NIL
2 | 7 | Risk of team member joining group | HR | PM will have to get new member up to date and allocate them roles | Christie | L | L | NIL
3 | 1 | Risk of scope requirements not met | Deliverable | Weekly meetings for updating and tracking progress | Danial, Whye Keat | M | H | NIL
4 | 8 | Risk of exceeding budget | Finance | Properly manage finance | Hui Min | L | L | NIL
5 | 2 | Risk of not meeting project schedule | Administrative | Track the progress of project weekly | Hui Min | L | H | NIL
6 | 3 | Risk of overall poor project quality | Deliverable | Conduct more quality checks of project inputs and outputs | Tian Sheng, Yong Qi | L | H | NIL
7 | 4-Delete when risk is solved | Risk of failed implementation of new project specs | Technology | Break down the requirements of the new specifications prior to coding to make sure that what is needed is clear | Danial, Whye Keat | M | H | NIL
8 | 5-Delete when risk is solved | Risk of failed integration of new project specs | Technology | Ensure the new implementation works as a standalone before trying to intergrate it into the current program | Danial, Whye Keat | H | H | NIL
9
Risk Register for Webook V3
Date 01/11/21
Project Name: Webook
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 6 | Risk of team member leaving from group | HR | Each member is paired with a secondary role as a contigency | Christie | L | H | NIL
2 | 7 | Risk of team member joining group | HR | PM will have to get new member up to date and allocate them roles | Christie | L | L | NIL
3 | 1 | Risk of scope requirements not met | Deliverable | Weekly meetings for updating and tracking progress | Danial, Whye Keat | M | H | NIL
4 | 8 | Risk of exceeding budget | Finance | Properly manage finance | Hui Min | L | L | NIL
5 | 2 | Risk of not meeting project schedule | Administrative | Track the progress of project weekly | Hui Min | L | H | NIL
6 | 3 | Risk of overall poor project quality | Deliverable | Conduct more quality checks of project inputs and outputs | Tian Sheng, Yong Qi | L | H | NIL
7 | 4-Delete when risk is solved | Risk of failed implementation of new project specs | Technology | Break down the requirements of the new specifications prior to coding to make sure that what is needed is clear | Danial, Whye Keat | M | H | NIL
8 | 5-Delete when risk is solved | Risk of failed integration of new project specs | Technology | Ensure the new implementation works as a standalone before trying to intergrate it into the current program | Danial, Whye Keat | H | H | NIL
Risk Register for Webook V4 Final
Date 08/11/21
Project Name: Webook
ID No. | Rank | Risk | Category | Potential Responses | Risk Owner | Probability | Impact | Residual Risk
1 | 4 | Risk of team member leaving from group | HR | Each member is paired with a secondary role as a contigency | Christie | L | H | NIL
2 | 5 | Risk of team member joining group | HR | PM will have to get new member up to date and allocate them roles | Christie | L | L | NIL
3 | 1 | Risk of scope requirements not met | Deliverable | Weekly meetings for updating and tracking progress | Danial, Whye Keat | M | H | NIL
4 | 6 | Risk of exceeding budget | Finance | Properly manage finance | Hui Min | L | L | NIL
5 | 2 | Risk of not meeting project schedule | Administrative | Track the progress of project weekly | Hui Min | L | H | NIL
6 | 3 | Risk of overall poor project quality | Deliverable | Conduct more quality checks of project inputs and outputs | Tian Sheng, Yong Qi | L | H | NIL